## Sheet1
Task Breakdown
Task Number | Task Description | Date Due (Planned) When you intend to complete the task | Date Completed (Actual) When you actually completed the task
1 | Review client requirements and existing website content | 2024-12-03 | 2024-12-03
2 | Create user stories | 3/14/2024 | 3/15/2024
3 | Develop design guide with logo color palette and fonts | 3/16/2024 | 3/18/2024
4 | Create wireframes for all website pages | 3/19/2024 | 3/19/2024
5 | Develop initial version of home page with HTML/CSS | 3/19/2024 | 3/19/2024
6 | Research and plan JavaScript libraries and widgets to use | 3/19/2024 | 3/19/2024
7 | Document JavaScript implementation plans | 3/19/2024 | 3/19/2024
8 | Finalize website content and copy | 3/24/2024 | 2024-01-04
9 | Develop remaining website pages with HTML/CSS | 3/28/2024 | 2024-01-04
10 | Implement JavaScript libraries and widgets | 3/28/2024 | 2024-01-04
11 | Add contact form and Google Maps integration | 3/29/2024 | 2024-01-04
12 | Optimize images and add citations | 3/29/2024 | 2024-01-04
13 | Conduct accessibility audit and make necessary improvements | 3/29/2024 | 2024-01-04
14 | Perform user testing and gather feedback | 3/30/2024 | 2024-01-04
15 | Implement design changes based on user feedback | 3/31/2024 | 2024-02-04
16 | Finalize user centered analysis and design documentation | 3/31/2024 | 2024-02-04
17 | Review and refine code organization and comments | 3/31/2024 | 2024-02-04
18 | Perform final testing and bug fixes | 3/31/2024 | 2024-02-04
19 | Prepare and submit final deliverables | 3/31/2024 | 2024-02-04